## Manual Chart
GANTT CHART FTC Robo Phantoms
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
Compliant Wheel Project
| Research | 2023-10-29 | 2023-11-04 | 5 | Dhruv/Kayan | 100%
| Drawing/CAD | 2023-11-04 | 2023-11-11 | 5 | Dhruv/Kayan | 50% | bar: WEEK 1 M to WEEK 1 W
| Get Parts/Prototype assembly | 2023-11-11 | 2023-11-18 | 5 | Dhruv/Kayan | 60%
| Build Prototype | 2023-11-18 | 2023-11-25 | 5 | Dhruv/Kayan | 0% | bar: WEEK 2 M
| Code | 2023-11-25 | 2023-12-02 | 5 | Dhruv/Kayan | 0% | bar: WEEK 2 M to WEEK 2 W
| Mount/Test | 2023-12-02 | 2023-12-16 | 10 | Dhruv/Kayan | 0%
Surgical Tubing Project
| Research | 2023-10-29 | 2023-11-04 | 5 | Harsh/Kavin | 100%
| Drawing/CAD | 2023-11-04 | 2023-11-11 | 5 | Harsh/Kavin | 50% | bar: WEEK 1 M to WEEK 1 W
| Get Parts/Prototype assembly | 2023-11-11 | 2023-11-18 | 5 | Harsh/Kavin | 60%
| Build Prototype | 2023-11-18 | 2023-11-25 | 5 | Harsh/Kavin | 0%
| Code | 2023-11-25 | 2023-12-02 | 5 | Harsh/Kavin | 0%
| Mount/Test | 2023-12-02 | 2023-12-16 | 10 | Harsh/Kavin | 0%
Claw Project
| Research | 2023-10-29 | 2023-11-04 | 5 | Ajay/Srilakshminath | 100%
| Drawing/CAD | 2023-11-04 | 2023-11-11 | 5 | Ajay/Srilakshminath | 50%
| Get Parts/Prototype assembly | 2023-11-11 | 2023-11-18 | 5 | Ajay/Srilakshminath | 60%
| Build Prototype | 2023-11-18 | 2023-11-25 | 5 | Ajay/Srilakshminath | 0%
| Code | 2023-11-25 | 2023-12-02 | 5 | Ajay/Srilakshminath | 0%
| Mount/Test | 2023-12-02 | 2023-12-16 | 10 | Ajay/Srilakshminath | 0%
Autonomous Project
| Park at Backstage | 2023-11-04 | 2023-11-11 | 5 | Ajay/Kavin | 0%
| Put the pixels at backstage and Park | 2023-11-11 | 2023-11-18 | 5 | Ajay/Kavin | 0%
| Put the pixels at backdrop and Park | 2023-11-18 | 2023-11-25 | 5 | Ajay/Kavin | 0%
| Put the purple pixel next to team prop | 2023-11-25 | 2023-12-02 | 5 | Ajay/Kavin | 0%
| Match the spike mark | 2023-12-02 | 2023-12-09 | 5 | Ajay/Kavin | 0%
| Put the white pixels | 2023-12-09 | 2023-12-16 | 5 | Ajay/Kavin | 0%
Arm Project
| Research | 2023-10-29 | 2023-11-04 | 5 | Kayan/Srilakshminath | 100%
| Drawing/CAD | 2023-11-04 | 2023-11-11 | 5 | Kayan/Srilakshminath | 0%
| Get Parts/Prototype | 2023-11-11 | 2023-11-18 | 5 | Kayan/Srilakshminath | 0%
| Build Prototype | 2023-11-18 | 2023-11-25 | 5 | Kayan/Srilakshminath | 0%
| Code | 2023-11-25 | 2023-12-02 | 5 | Kayan/Srilakshminath | 0%
| Mount/Test | 2023-12-02 | 2023-12-16 | 10 | Kayan/Srilakshminath | 0%
Drone/Hanging Project
| Research | 2023-10-29 | 2023-11-04 | 5 | Dhruv/Harsh | 100%
| Drawing/CAD | 2023-11-04 | 2023-11-11 | 5 | Dhruv/Harsh | 0%
| Get Parts/Prototype | 2023-11-11 | 2023-11-18 | 5 | Dhruv/Harsh | 0%
| Build Prototype | 2023-11-18 | 2023-11-25 | 5 | Dhruv/Harsh | 0%
| Code | 2023-11-25 | 2023-12-02 | 5 | Dhruv/Harsh | 0%
| Mount/Test | 2023-12-02 | 2023-12-16 | 10 | Dhruv/Harsh | 0%
Formulas:
DURATION (WORK DAYS) = NETWORKDAYS([START DATE],[END DATE])